## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | [7 empty] | Total | Critical | High | Moderate | Low | Negligible
[9 empty] | Risk | 4 | 0 | 0 | 0 | 0 | 0 | Instruction to use the RAID log template: • All fields must be duly filled • The descriptions for what to be filled in each of the fields are provided in the template. • Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes. • Understand what risks, assumptions, issues, and dependencies are from the description provided in the methodology document • Select the category of RAID from the dropdown menu provided in the “RAID category” field in the template. • Provide a valid description of the RAID category that you have selected in the “description” field provided. • Describe the impact the RAID category you have selected will have on the project in the “impact field”. • Describe how the impact of the selected RAID category can be reduced on the project in the “mitigation field” in the template. • Mention the responsible person for working on the selected RAID category in the “owner” field in the template. • Select the priority with which the selected RAID category needs to be mitigated. The following levels of priority are given in the drop-down menu. Select; o Negligible: if the RAID category is not going to make an impact on the project o Low: if the raid category is going to make very small impacts on the project o Moderate: if the RAID category is going to make a few impacts which can affect the project adversely. o High: if the RAID category is going to make major impacts on the project adversely. o Critical: if the raid category is going to affect the project at any stage. • Provide risk priority number based on the priority selected for the RAID category selected. • Select the status of the RAID category selected. Two options are provided in the drop-down menu. Select; o Open: if the responsible person is still working on the RAID category selected. o Closed: if the responsible person has worked on the RAID category and is solved.
| Project title: | Absence of Insights – StudentSalaryScope (Data Analytics) |  | Project Id: | IP-11635 | Project Manager: | Harshada Topale |  | Assumption | 3 | 0 | 0 | 0 | 0 | 0
[9 empty] | Issue | 2 | 0 | 0 | 0 | 0 | 0
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2026-08-09 | Project Team Lead: | Jatin Rathod |  | Dependency | 2 | 0 | 0 | 0 | 0 | 0
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  | 11 |  |  |  |  | 0
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Data quality issues —Leadership Skills values are inconsistent due to case and whitespace differences. | Incorrect grouping in leadership analysis;May cause inaccurate grouping and EDA results. | Applied .str.strip().str.lower() to Leadership column before all analysis. Standardized Leadership Skills values before analysis. | Jatin Rathod | High | 6 | Closed
2 | Risk | Time management conflict —Academic commitments may affect internship project timelines. | May delay analysis and project completion. | Prioritized tasks and tracked progress against the schedule. | Jatin Rathod | Moderate | 4 | Closed
3 | Risk | Misinterpretation of analytical questions may lead to incorrect analysis. | Delivering wrong metric or incorrect grouping logic may result in incorrect conclusions. | Reviewed each question and validated results before finalizing. | Jatin Rathod | High | 5 | Closed
4 | Risk | Python library or tool compatibility issues may affect analysis. | Blocked progress on analysis tasks; may interrupt notebook execution and visualizations. | Used compatible library versions and tested notebook execution. | Jatin Rathod | Low | 2 | Closed
5 | Assumption | The provided dataset will remain complete and unchanged during the project. | If the dataset were updated mid-project, previous analysis results would become invalid requiring a full re-run of all 16 questions and 16+ visualizations | Verified dataset consistency before performing analysis. | Jatin Rathod | Moderate | 3 | Closed
6 | Assumption | Student Email IDs are already anonymized by Cloud Counselage. | If the dataset contained real email addresses, sharing it for analysis would constitute a privacy violation requiring immediate data remediation | Used only anonymized student identifiers for analysis. | Jatin Rathod | Low | 1 | Closed
7 | Assumption | Free tools are sufficient to complete the project requirements. | If free tool limitations were hit (e.g., Colab session timeouts, Power BI row limits), certain deliverables may get delayed | Used available free tools and optimized the workflow accordingly. | Jatin Rathod | Low | 2 | Closed
8 | Issue | 4,894 records contain only 2,157 unique students due to repeated event registrations. | Overcounting students in analyses requiring unique student counts, inflated averages if duplicates not removed; may bias student-level analysis if duplicates are ignored. | Identified duplicate student registrations before student-level analysis. | Jatin Rathod | High | 5 | Closed
9 | Issue | Promotion Channel contains 2,216 missing values, limiting participation analysis. | Q15 (Which promotion channel brings in more participation?) could only be answered for the 54% of respondents who filled the field — results are not representative of the full dataset | Handled missing values appropriately and documented the limitation. | Jatin Rathod | Moderate | 4 | Closed
10 | Dependency | Project execution depends on completion and approval of planning documents. | Delays may affect overall project progress. Delays in planning documents directly delay execution start date. | Completed required planning documents as per the project schedule. | Jatin Rathod | High | 5 | Closed
11 | Dependency | Project completion depends on successful submission and approval of all deliverables. | Delayed approval may affect project closure. | Reviewed and submitted all deliverables within the required timeline. | Jatin Rathod | Critical | 7 | Closed
17
18
19
20
21
22
23
24