## Sheet1
IAC REQUIREMENT ELICITATION QUESTIONNAIRE
Intern Name: | Jatin Rathod
Selected Domain: | Data Analytics
Domain Problem/Project name: | Absence of Insights - StudentSalaryScope
Meeting Date & Time | 14-Jun-2026 ¦ 11:00 AM IST
Meeting Venue/ Link: | Microsoft Teams Virtual Meeting
Stakeholders Present in the Meeting: | Project Manager, Cloud Counselage, Domain Lead — Data Analytics (IAC), Jatin Rathod (Intern)
This questionnaire is to be used by the consultant to gather requirements from the client
QUESTIONS | ANSWERS
General Inquiry
What do you hope to accomplish with the proposed project? | Perform EDA on 4,894 student records to identify relationships between background, academics, skills, and expected salary.
How do the project/system’s goals map to the department goals or needs? | Provides data-driven insights for career guidance, skill development, city targeting, and event promotion.
What will the project accomplish that is not currently accomplished manually or with other projects/software? | Creates the first structured analysis of the dataset with automated insights and visualizations.
Are there other projects/systems with which this project/system will interface? | Uses the IAC platform, Google Colab/Jupyter Notebook, and Power BI.
Is there any existing project/system documentation? | GPI Problem Statement, dataset, and GPI Live Project Instructions.
Current Needs and Problems
What department/business requirements will this project/system address? | Identify student profiles, salary factors, high-performing cities, and effective promotion channels.
Is any of this data currently captured in any other project/system?  Is the data and/or functionality shared by others? | Raw data exists in IAC as an Excel file but has not been previously analyzed.
What problems should this project/system solve? | The absence of structured insights means that career advisors and domain leads cannot identify which student profiles are most likely to succeed, or what interventions could improve outcomes for students from lower-income families.
Do you have to do things manually that you would like to automate | Yes. Data cleaning, aggregation, and cross-tabulation of student attributes are currently done manually, These processes need to be automated through Python and visualized through BI dashboards.
Do you have performance problems that need to change? | Reduces time-consuming manual analysis of 4,894 records through automated computation.
Do you have functional limitations that you’d like to change? | Yes. Currently there is no visualization layer whatsoever — all data is in raw spreadsheet format with no charts, filters, KPI summaries, or trend indicators.
What will this project/system do that is entirely new? | This project will be the first-ever analytical initiative on this dataset —Provides automated student-level, city-level, income, competency, and promotion analysis
Criteria for success
What is most important for success of the project? | The single most important success criterion is: all 16 analytical questions answered accurately with supporting visualizations and written conclusions, clearly interpretable by anyone.
What are the training considerations? | Requires basic Python, statistics, visualization, and Jupyter/Colab knowledge.
What resources might be needed (budget, staff, etc) | One intern, Python/Colab, dataset, IAC access, and approximately 240+ hours.
Are there any dependencies on other project/system in completing the project/system? | Yes. The project has two key dependencies: (1) The dataset must be provided by Cloud Counselage before EDA can begin. (2) Project initiation documents (Charter, REQ Questionnaire, SRS) must be completed before execution begins.
Are there resource constraints in maintaining the project/system? | Limited to 240 hours over 8 weeks and individual execution.
Do you have the in-house expertise we need? | Yes. Intern has demonstrated experience in Python data analysis (Pandas, Matplotlib) through prior academic projects. Domain expertise in exploratory data analysis, statistical interpretation, and visualization is available and has been validated through previous coursework and projects.
Are there technical constraints to developing this project/system? | Only free/open-source tools and the provided dataset can be used.
What needs to happen to make this project/system successful? | Clear question understanding, proper cleaning, validation, documentation, and timely reviews.
Finding Stakeholders
Who are the key stakeholders and users? | Project Sponsor, Project Manager, Domain Lead, and Intern/Data Analyst.
Do their goals differ? If so, how? | Sponsor focuses on outcomes, PM on completion, Domain Lead on quality, and Intern on execution.
Who uses the system? | Primary user: Jatin Rathod (intern), Domain Lead, Project Manager, and Project Sponsor.
Who installs the system? | No installation for Colab/IAC; Power BI requires local installation if used.
Who trains people to use the system? | Training comes through the IAC course, domain guidance, and self-learning.
Who fixes the system? | The intern (Jatin Rathod) is responsible for identifying and fixing errors in analysis code, with domain lead and PM support when required.
Who maintains the system? | Cloud Counselage maintains the source data/IAC platform; the intern maintains analysis outputs.
Who creates, updates, deletes information in the system? | Cloud Counselage manages source data; the intern creates analytical outputs.
What other systems interface with the system? | IAC, Google Colab/Jupyter, Power BI, Excel, and GitHub.
Who gets information from this system? | Domain Lead, Project Manager, Project Sponsor, and future career-focused users.
Who provides information to the system? | Cloud Counselage provides the dataset; the intern provides analysis and reports.
Are there are others they believe should be involved in the process of identifying the project requirements? | Future interns, academic mentors, and career counselors may use the findings.
Whats the process
What is the purpose of this process? | Convert raw student records into actionable insights on skills, academics, background, and salary.
What triggers this process to start? | Receipt of the dataset and Problem Statement after project initiation.
Who is responsible to perform this process? | Jatin Rathod (Intern) is solely responsible for executing the analysis, with oversight from the Domain Lead and PM.
How does this process work today? | Analysis is currently performed manually using the raw Excel dataset.
What is the end result or output of this process? | A fully documented Jupyter Notebook (.ipynb) containing: (1) data loading and profiling code, (2) cleaning and preprocessing steps, (3) 16 answered analytical questions with Python code and chart outputs, (4) written conclusions per question, and (5) a summary table of all key findings.
Is there a system that supports this process today? | No formal analytical system currently exists.
If there is a system, are you able to show us how this system works? | Not applicable because no existing analytical system exists.
If there is a system, are you able to provide us with some screen shots from this system? | Raw dataset screenshots can be provided if required.
If there is a system, are you able to refer us to where we can find the user guide for this system? | No formal analytical system user guide currently exists.
Reports
Do you currently have any existing operational reports which help you manage this team? | No existing analytical reports are available for this dataset.
Are you able to tell us about your most important reports? | Key outputs include GPA, income, Python experience, promotion, city, and salary analyses.
Which systems produce your reports for you? | Reports are generated using Python, Matplotlib/Seaborn, and optionally Power BI.
How often to you receive these reports? | Weekly progress reports and one final report at project completion.
Are you able to share some examples of these reports with me/ us? | CGPA distribution, income analysis, college GPA, promotion channels, and competency-salary charts.
Tell us about some of your reporting requirements. What would you really like to see produced as a report? Why? | Stakeholders need student, GPA, income, competency, promotion, and salary insights.
Discuss the content, frequency, audience and layout of the report at a high level. | Charts, code, conclusions, and summaries delivered through weekly and final reports.
Identifying use cases
What functions will the users want from the system? | Analyze student counts, CGPA, income, skills, salary, cities, promotion channels, and outliers.
Does the system store information? | Source data is stored in Excel; analysis outputs are stored in Colab/GitHub and final submissions on IAC.
Do the users need to create, update, or delete information? | No source-data CRUD operations are required
Does the system need to notify a user about changes in an internal state? | No notifications are required because this is a static batch EDA project.
Are there any external events the system must know about? | No external events trigger the analysis.
What is the user’s overall job? | Perform data cleaning, EDA, visualization, interpretation, documentation, and submission.
What problems have the users had in the past? | Previously, stakeholders had no visibility lacked structured insights into student competencies, salary expectations, and outreach effectiveness.
What steps are manual today? | Sorting, filtering, calculations, and chart creation are replaced by automated Python analysis.