## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME:
INTERN NAME:
PROJECT NAME:
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | DD-MMM-YYYY
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments may be added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled
5. The descriptions for what to be filled in each of the fields are provided in the template.
6. Clear all the sample data/instructions provided in the template. The data/instruction provided is only for reference purposes.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | StudentSalaryScope
PROJECT ID | IP-11635
PROJECT MANAGER | Harshada Topale – Director, Cloud Counselage Pvt. Ltd.
PROJECT SPONSOR | Tushar Topale – Director, CC-GAC Foundation
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
| MENTION THE DATE ON WHICH THE MATTER WAS RAISED | DESCRIBE THE EVENT THAT WAS RAISED | MENTION WHICH CATEGORY THE EVENT WAS RELATED TO | MENTION YES OR NO | MENTION THE RECOMMENDATIONS THAT WAS SUGGESTED FOR SOLVING THE EVENT IF ANY | MENTION THE ACTION SELECTED FOR SOLVING THE VENT | MENTION THE RESPONSIBLE PERSON FOR SOLVING THE EVENT | SOLVED/ PENDING | MENTION IF ANYTHING ELSE OCCURRED DURING THE TIME OF THE MENTIONED EVENT
1 | 2026-06-09 | Data Profiling | Uniqueness checks on key columns are essential before starting analysis. | Yes | Always run a uniqueness check on the primary key column at the start of any EDA. | Split the data into df (4,894 rows) and df_unique (2,157 rows) and used the correct one per question. | Jatin Rathod | Closed | df.shape showed 4,894 rows, but only 2,157 were unique students.
2 | 2026-06-09 | Data Cleaning | Categorical text columns should always be cleaned before analysis. | Yes | Standardize text columns (strip whitespace, fix casing) before any grouping or counting. | Cleaned the Leadership Skills column using str.strip().str.lower(). | Jatin Rathod | Closed | Column had mixed values like "Yes", "yes ", "No " instead of just two.
3 | 2026-06-12 | Milestone Planning | Timelines should account for other academic commitments. | Yes | Map actual available hours per day before setting milestone dates. | Revised schedule to 2-3 working hours/day with buffer days, and informed the domain lead. | Jatin Rathod | Closed | Original plan assumed full-time availability, which wasn't realistic alongside college.
4 | 2026-06-14 | Elicitation Meeting | Clarifying requirements early avoids rework later. | Yes | Confirm data-level distinctions with the domain lead before starting. | Documented the df vs df_unique distinction clearly in the notebook. | Jatin Rathod | Closed | Meeting resolved ambiguity in how "students" was used in the Problem Statement.
5 | 2026-06-17 | SRS Review | Requirements should be specific and traceable, not vague. | Yes | Write one functional requirement per analytical question for traceability. | Rewrote the SRS with 23 numbered functional requirements (FR-01 to FR-23). | Jatin Rathod | Closed | First draft was too generic and got sent back by the domain lead.
6 | 2026-07-08 | Data Analysis (Q15) | Null values should always be checked and disclosed transparently. | Yes | Always check for nulls with dropna=False before drawing conclusions from a column. | Documented that ~45% of the promotion channel column was missing and qualified the finding accordingly. | Jatin Rathod | Closed | Missing values weren't mentioned in the Problem Statement, so this needed flagging.
7 | 2026-07-06 | Outlier Detection (Q7) | IQR detected **zero outliers** because all students had Quantity = 1, | No | Report what the data shows without forcing expected outcomes. | Verified using box plot and distribution chart. | Jatin Rathod | Closed | Zero outliers was a valid data finding.
8 | 2026-07-06 | College GPA Ranking (Q6) | Colleges with 1–2 students had misleading 10.0 GPA averages. | Yes | Apply a minimum sample-size filter. | Used 5-student minimum; identified St Xavier's and New Horizon as top colleges. | Jatin Rathod | Closed | Sample size is important for fair comparisons.
9 | 2026-07-07 | EDA Notebook Assembly | Out-of-order cells caused KeyError during clean execution. | Yes | Always use Restart and Run All before submission. | Reordered cells and completed 3 clean tests. | Jatin Rathod | Closed | Clean runtime testing prevents notebook errors.
10 | 2026-07-08 | GPA vs Salary Correlation (Q11) | Pearson r = 0.178 showed a weak GPA-salary relationship. | No | Report weak correlations accurately. | Documented r = 0.178 and compared it with Python experience. | Jatin Rathod | Closed | Python experience showed stronger salary correlation.
11 | 2026-07-10 | Field Categorization (Q12) | Designation variants caused missed categories initially. | Yes | Review and refine uncategorized values. | Created categorize_field() with 6 keyword categories. | Jatin Rathod | Closed | Keyword categorization is useful for free-text cleaning.
12 | 2026-07-13 | Leadership Skills Analysis (Q13) | Leadership groups had nearly identical GPA and salary. | No | Use a more detailed leadership scale than yes/no. | Recommended a 1–5 leadership rating for future data collection. | Jatin Rathod | Closed | The finding highlighted a survey-design limitation.
13 | 2026-07-20 | Quadrant Segmentation (Q17) | Arbitrary thresholds created highly unbalanced groups. | Yes | Use median-based thresholds. | Created balanced quadrants; High CGPA + High Python had 14.74L average salary. | Jatin Rathod | Closed | Median segmentation produced a strong actionable insight.
14 | 2026-07-25 | City GPA Chart (Q8) | 200+ cities made the chart unreadable. | Yes | Limit charts to Top N with minimum sample size. | Used top 15 cities with at least 3 students. | Jatin Rathod | Closed | Large datasets benefit from interactive dashboards.
15 | 2026-08-01 | Power BI Dashboard | Building the dashboard later caused metric rework in DAX. | No | Develop Power BI alongside EDA. | Created 5 KPI cards, 6 charts, drill-through and tooltips. | Jatin Rathod | Closed | Parallel development reduces rework
16 | 2026-08-05 | Weekly Progress Reports | Retrospective reporting made activity recall difficult. | Yes | Maintain daily notes. | Started documenting activities for the IAC Journaling App. | Jatin Rathod | Closed | Daily journaling improves reporting accuracy.
17 | 2026-08-06 | IAC Submission | Inconsistent file names caused upload confusion. | No | Follow a consistent naming format. | Renamed all 8 files and verified the submission checklist. | Jatin Rathod | Closed | Professional naming improves final submission quality.
18 | 2026-08-09 | Document Review | Final review found inconsistent milestone and deliverable counts. | No | Cross-check all project documents. | Reviewed 8 documents and fixed 3 inconsistencies. | Jatin Rathod | Closed | Cross-document consistency is essential before submission.