## GPI - Project Charter
PROJECT CHARTER
GENERAL PROJECT INFORMATION
PROJECT NAME | StudentSalaryScope
PROJECT SPONSOR | Tushar Topale – Director, CC-GAC Foundation
PROJECT MANAGER | Harshada Topale – Director, Cloud Counselage Pvt. Ltd.
EXPECTED START DATE | 2026-06-08
EXPECTED COMPLETION DATE | 2026-08-03
ESTIMATED COST | N.A.
GOALS, OBJECTIVES, DELIVERABLES
PROJECT OBJECTIVE (Objective of a project represents the output or what you want to accomplish by doing it.) | To perform EDA on 4,894 student records to identify key relationships between academic performance, skills, background, and expected salary, supported by 16 analytical questions, visualizations, and complete project documentation.
BUSINESS CASE (A business case provides justification for undertaking a project. It evaluates the benefit, cost and risk of alternative options and provides a rationale for the preferred solution. ) | The project analyzes student records to uncover how economic background, academic performance, technical skills, and location influence employability and salary expectations. It provides actionable insights for targeted career support, competency development, event promotion, and geographic talent analysis.
GOALS/METRICS (The project goal refers to achieving a desired outcome (performance goal) at a specific end date (time goal) employing a specific amount of resources (resource goal).) | • Complete EDA of 4,894 records • 16 analytical questions answered • Supporting charts & insights • Multi-panel visualizations • Complete GPI documentation • 120-hour project completion • On-time IAC submission • Zero plagiarism
EXPECTED DELIVERABLES (Describe the quantifiable goods or services that must be provided upon the completion of a project.) | 1. Project Charter (this document) 2. Requirement Elicitation Questionnaire 3. Software Requirements Specification (SRS) 4. Work Breakdown Structure (WBS) 5. Project Schedule / Gantt Chart 6. RAID Log 7. Lessons Learnt Log 8. EDA Jupyter Notebook (DA_GPI_Analysis_JatinRathod.ipynb) 9. Final Project Report 10. Analytics Dashboard (Power BI )
PROJECT SCOPE AND SCHEDULE
WITHIN SCOPE (This is functions and information which should be taken into account(estimated) in the development at the first stage. Or the stage for the development perios.) | 1. Exploratory Data Analysis (EDA) of the provided student dataset (4,894 rows × 16 columns) 2. Answering all 16 analytical questions from the Problem Statement (8 Basic + 8 Moderate) 3. Data profiling, cleaning, and preprocessing (null handling, deduplication, column standardization) 4. Visualizations using Python (Matplotlib, Seaborn) in Google Colab / Jupyter Notebook 5. Statistical analysis: distributions, correlations, outlier detection, group comparisons, quadrant analysis 6. Complete project documentation: Charter, REQ Questionnaire, SRS, WBS, Project Schedule, RAID Log, Lessons Learnt Log, and Final Project Report 7. Weekly progress reporting on the IAC platform 8. Analytics Dashboard (Python charts or Power BI visuals embedded in the notebook)
OUTSIDE OF SCOPE (This is functions which are planned to be done, but they are not reqired on the first stages.) | 1. Building a predictive Machine Learning model (regression, classification, or clustering) 2. Collecting new primary data beyond the provided IAC dataset 3. Deployment of any application to cloud infrastructure (AWS, GCP, Azure, Heroku) 4. Use of any paid tools, APIs, or licensed software 5. Real-time data integration or streaming analysis 6. Web application or mobile app development 7. Database design or backend system development
PROJECT RESOURCES AND COSTS
PROJECT TEAM (Mention the number of resources, who will be working on the project.) | Intern / Data Analyst: Jatin Rathod (IP-11635) Domain Lead — Data Analytics, IAC: Project Manager: Harshada Topale, Cloud Counselage Pvt. Ltd.
SUPPORT RESOURCES (Mention all the other resources that will be needed for the completion of the project.) | 1. Python 3.10+ — Primary analysis language 2. Google Colab / Jupyter Notebook — Cloud-based development environment 3. Pandas 2.0+ — Data manipulation and aggregation 4. Matplotlib 3.7+ / Seaborn 0.12+ — Data visualization 5. NumPy 1.24+ — Numerical computations 6. Power BI Desktop (free version) — Business intelligence dashboard 7. Microsoft Excel — Dataset source and template management 8. GitHub — Version control and code repository 9. IAC Platform — Submission portal and weekly reporting
COST ALLOCATION (Mention the cost of all the resources on an hourly/monthly/yearly basis. This will help to stick on to the project budget.) | N.A.
PROJECT STAKEHOLDERS AND CUSTOMERS
PROCESS OWNER (Mention the Project Owner) | Cloud Counselage Pvt. Ltd. & Industry Academia Community (IAC) — Gift-A-Career (CC-GAC) Foundation
KEY STAKEHOLDERS (Mention all the stake holders involved in the project.) | 1. Tushar Topale — Director, CC-GAC Foundation ¦ Role: Project Sponsor 2. Harshada Topale — Director, Cloud Counselage Pvt. Ltd. ¦ Role: Project Manager 3. Domain Lead — Data Analytics, IAC ¦ Role: Technical Reviewer 4. Jatin Rathod — B.Tech IT Student, VIT Wadala ¦ Role: Intern / Data Analyst
END CUSTOMER (Mention the client name.) | Cloud Counselage Pvt. Ltd. ( Foundation Internship Program)
PROJECT RISKS, CONSTRAINTS, ASSUMPTIONS
RISKS (Risk is any unexpected event that can affect your project — for better or for worse. Risk can affect anything: people, processes, technology, and resources.) | R1 [High] — Data Quality Issues: Missing values, inconsistent formatting in Leadership Skills column ('yes', 'Yes ', 'yes '). Mitigation: Thorough data cleaning with .str.strip().str.lower() before any analysis. R2 [Moderate] — Time Management: Balancing internship with VIT Wadala academic commitments. Mitigation: 2–3 hrs/day dedicated schedule with buffer days built in. R3 [High] — Question Misinterpretation: Answering wrong metric or using wrong grouping logic for the 16 analytical questions. Mitigation: Re-read each question before coding; validate against expected column logic. R4 [Low] — Tool Compatibility: Python library version conflicts or Power BI rendering issues. Mitigation: Use Google Colab (standardized Python 3.10 environment) for all coding.
ASSUMPTIONS (An assumption is any project factor that is considered to be true, real, or certain without empirical proof or demonstration.) | A1: The provided dataset (Power_BI_Updated_Data_analyst_Data.xlsx — 4,894 rows, 16 columns) is complete, accurate, and will not change during the project duration. A2: Email IDs in the dataset are properly anonymized (replaced with @xyz.com format) — no additional privacy/GDPR handling is required. A3: Free tools (Google Colab, Power BI Desktop free, Python open-source libraries) are fully sufficient to produce all required deliverables. A4: The intern has foundational Python and data analysis skills adequate to complete the project independently. A5: Weekly domain lead meetings will be available for guidance and feedback throughout the project.
CONSTRAINTS (Project constraints are anything that restricts or dictates the actions of the project team.) | C1: Only open-source/free/trial tools and platforms may be used — no paid software or APIs permitted. C2: This is an individual project — collaboration or sharing of deliverables with other interns is strictly prohibited. C3: All work produced is the intellectual property of Cloud Counselage Pvt. Ltd. C4: Minimum 240 hours of engagement is required for the experience letter to be issued. C5: All submissions must adhere to deadlines set by the domain lead on the IAC platform. C6: The analysis must be based solely on the provided dataset — no external data sources may be used.
MILESTONES
MILESTONE 1- Requirement Gathering ("Mention Completion Date in MM-DD-YYYY format. Requirement gathering is marked as complete after submission of SRS document")
MILESTONE 2 - Planning ("Mention Completion Date in MM-DD-YYYY format. Planning phase is considered after a duly completed Work Breakdown Structure (WBS), Project Schedule and RAID logs")
MILESTONE 3 - Design ("Mention Completion Date in MM-DD-YYYY format. Design stage is considered complete after submission of Design Specifications and Wireframe files")
MILESTONE 4 - Development ("Mention Completion Date in MM-DD-YYYY format. Development stage is considered complete after submission of Design Specifications and Wireframe files")
MILESTONE 5 - Testing ("Mention Completion Date in MM-DD-YYYY format. Testing stage is considered complete after submission of Test Reports")
MILESTONE 6 - Deployment ("Mention Completion Date in MM-DD-YYYY format. Deployment stage is considered complete after sybmitting the ")
MILESTONE 7 - Closure ("Mention Completion Date in MM-DD-YYYY format. Project closure is considered complete after handover of leasson learnt log, project report and installation guide")