## Guide
IAC GLOBAL PROFESSIONAL INTERNSHIP
DOCUMENT TITLE: | PROJECT SCHEDULE
Document created By: | Jatin Rathod
Document Created On: | 08-Jun-2026
Version: | 1
Instructions:
1. Create a project schedule based on your Work Breakdown structure
2. You may refer the 'Example' tab. Activities & Task to be included in the schedule will vary based on your selected domain
3. You may group/ expand/collapse the set of activities
4. Please rename the file as 'IAC IP23 - your Domain Name - Project Schedule - Your Full Name'
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop

## Project Schedule
IAC Internship Program 2026 - Data Analytics Project Schedule - Jatin Rathod
|  | PROJECT START DATE | 2026-06-08 | 2026-06-09
|  | Display Week Sr No | 1 | [10 empty] | 2026-06-08 | [6 empty] | 2026-06-15 | [6 empty] | 2026-06-22 | [6 empty] | 2026-06-29 | [6 empty] | 2026-07-06 | [6 empty] | 2026-07-13 | [6 empty] | 2026-07-20 | [6 empty] | 2026-07-27 | [6 empty] | 2026-08-03
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop https://script.google.com/macros/s/AKfycbz1vCRZzDZf9SkwX8gv1DzKe59fupHWWehSUu0jeTsiZZxn3YdNVAD1sHDLDUanbJ5O/exec | time axis 2026-06-08 to 2026-08-09
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | Actual End Date | Hours required | Status | Progress | Comments | time axis 2026-06-08 to 2026-08-09
1 | Week 1 - Project Initiation |  |  |  |  | Jatin Rathod | 2026-06-08 | 2026-06-14 | 2026-06-14 |  | Completed | 100%
1.1 |  | GPI Onboarding |  |  |  | Jatin Rathod | 2026-06-08 | 2026-06-08 | 2026-06-08 | 4 | Completed | 100% | GPI program, IAC Pledge, Appointment Letter
1.1.1 |  | GPI Onboarding | Complete GPI Program on IAC |  |  | Jatin Rathod | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2 | Completed | 100%
1.1.2 |  | GPI Onboarding | IAC Pledge + Appointment Letter |  |  | Jatin Rathod | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2 | Completed | 100%
1.2 |  | Internship Preparation |  |  |  | Jatin Rathod | 2026-06-09 | 2026-06-09 | 2026-06-09 | 5 | Completed | 100% | SWOT, Career Vision, CV Building, Interview Prep
1.3 |  | Problem Statement & Dataset |  |  |  | Jatin Rathod | 2026-06-09 | 2026-06-09 | 2026-06-09 | 3 | Completed | 100% | 4,894 rows x 16 cols confirmed
1.3.1 |  | Problem Statement & Dataset | Read Problem Statement Document |  |  | Jatin Rathod | 2026-06-09 | 2026-06-09 | 2026-06-09 | 1 | Completed | 100%
1.3.2 |  | Problem Statement & Dataset | Load & Profile Dataset |  |  | Jatin Rathod | 2026-06-09 | 2026-06-09 | 2026-06-09 | 2 | Completed | 100% | Discovered 2,157 unique students vs 4,894 rows
1.4 |  | Requirement Elicitation |  |  |  | Jatin Rathod | 2026-06-10 | 2026-06-15 | 2026-06-15 | 8 | Completed | 100% | REQ Questionnaire - 7 sections, ~40 Q&As
1.4.1 |  | Requirement Elicitation | Started working on REQ |  |  | Jatin Rathod | 2026-06-10 | 2026-06-14 | 2026-06-14 | 2 | Completed | 100%
1.4.2 |  | Requirement Elicitation | Fill REQ Questionnaire |  | 1.4.1 | Jatin Rathod | 2026-06-14 | 2026-06-15 | 2026-06-15 | 6 | Completed | 100% | Submitted 15-Jun-2026
1.5 |  | Project Charter |  |  |  | Jatin Rathod | 2026-06-12 | 2026-06-14 | 2026-06-14 | 6 | Completed | 100% | Submitted 14-Jun-2026
1.5.1 |  | Project Charter | Define objectives, scope, milestones |  |  | Jatin Rathod | 2026-06-12 | 2026-06-13 | 2026-06-13 | 3 | Completed | 100%
1.5.2 |  | Project Charter | Fill & submit Charter template |  | 1.5.1 | Jatin Rathod | 2026-06-14 | 2026-06-14 | 2026-06-14 | 3 | Completed | 100%
1.6 |  | SRS Document |  |  | 1.5 | Jatin Rathod | 2026-06-15 | 2026-06-17 | 2026-06-17 | 5 | Completed | 100% | 23 Functional Requirements (FR-01 to FR-23)
1.6.1 |  | SRS Document | Fill all 14 SRS sections |  | 1.4 | Jatin Rathod | 2026-06-15 | 2026-06-17 | 2026-06-17 | 5 | Completed | 100% | Submitted 17-Jun-2026
2 | Week 2 - Project Planning |  |  |  |  | Jatin Rathod | 2026-06-15 | 2026-07-01 | 2026-07-01 |  | Completed | 100%
2.1 |  | Work Breakdown Structure |  |  | 1.6 | Jatin Rathod | 2026-06-18 | 2026-06-20 | 2026-06-20 | 4 | Completed | 100% | Submitted 20-Jun-2026
2.1.1 |  | Work Breakdown Structure | Define all phases and tasks |  |  | Jatin Rathod | 2026-06-18 | 2026-06-19 | 2026-06-19 | 2 | Completed | 100%
2.1.2 |  | Work Breakdown Structure | Create WBS SmartArt (PPTX) |  | 2.1.1 | Jatin Rathod | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2 | Completed | 100%
2.2 |  | Project Schedule |  |  | 2.1 | Jatin Rathod | 2026-06-21 | 2026-06-25 | 2026-06-25 | 5 | Completed | 100% | Submitted 25-Jun-2026
2.2.1 |  | Project Schedule | Map all tasks to timeline |  | 2.1 | Jatin Rathod | 2026-06-21 | 2026-06-25 | 2026-06-25 | 5 | Completed | 100% | 48 tasks across 8 weeks
2.3 |  | RAID Log |  |  | 2.2 | Jatin Rathod | 2026-06-26 | 2026-06-29 | 2026-06-29 | 4 | Completed | 100% | Submitted 29-Jun-2026
2.3.1 |  | RAID Log | Document 4 Risks, 3 Assumptions, 2 Issues, 2 Dependencies |  | 2.2 | Jatin Rathod | 2026-06-26 | 2026-06-29 | 2026-06-29 | 4 | Completed | 100% | 11 total entries
2.4 |  | Lessons Learnt Log |  |  | 2.3 | Jatin Rathod | 2026-06-30 | 2026-07-01 | 2026-07-01 | 3 | Completed | 100% | Submitted 01-Jul-2026
2.4.1 |  | Lessons Learnt Log | Document lessons from Initiation & Planning |  | 2.3 | Jatin Rathod | 2026-06-30 | 2026-07-01 | 2026-07-01 | 3 | Completed | 100% | 6 entries total
3 | Week 3-4 - Execution: EDA |  |  |  |  | Jatin Rathod | 2026-07-02 | 2026-07-08 | 2026-07-08 |  | Completed | 100%
3.1 |  | Data Loading & Profiling |  |  | 2 | Jatin Rathod | 2026-07-02 | 2026-07-02 | 2026-07-02 | 3 | Completed | 100% | 4,894 rows x 16 cols
3.1.1 |  | Data Loading & Profiling | Load dataset, inspect dtypes, nulls |  |  | Jatin Rathod | 2026-07-02 | 2026-07-02 | 2026-07-02 | 3 | Completed | 100%
3.2 |  | Data Cleaning |  |  | 3.1 | Jatin Rathod | 2026-07-03 | 2026-07-04 | 2026-07-04 | 5 | Completed | 100%
3.2.1 |  | Data Cleaning | Standardize Leadership column |  | 3.1 | Jatin Rathod | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2 | Completed | 100% | .str.strip().str.lower()
3.2.2 |  | Data Cleaning | Deduplicate on Email ID |  | 3.2.1 | Jatin Rathod | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2 | Completed | 100% | df_unique: 2,157 students
3.2.3 |  | Data Cleaning | Outlier Detection (IQR) |  | 3.2.2 | Jatin Rathod | 2026-07-04 | 2026-07-04 | 2026-07-04 | 1 | Completed | 100% | IQR=0, no outliers
3.3 |  | EDA - Basic Questions Q1-Q9 |  |  | 3.2 | Jatin Rathod | 2026-07-04 | 2026-07-06 | 2026-07-06 | 12 | Completed | 100% | All 9 basic questions answered
3.3.1 |  | EDA - Basic Questions Q1-Q9 | Q1-Q4: Unique students, avg GPA, grad year, Python dist |  | 3.2 | Jatin Rathod | 2026-07-04 | 2026-07-05 | 2026-07-05 | 6 | Completed | 100%
3.3.2 |  | EDA - Basic Questions Q1-Q9 | Q5-Q9: Income dist, college GPA, outliers, city GPA, income-GPA |  | 3.3.1 | Jatin Rathod | 2026-07-05 | 2026-07-06 | 2026-07-06 | 6 | Completed | 100% | Sample size filter applied Q6
3.4 |  | EDA - Moderate Questions Q10-Q17 |  |  | 3.3 | Jatin Rathod | 2026-07-06 | 2026-07-08 | 2026-07-08 | 12 | Completed | 100% | All 8 moderate questions answered
3.4.1 |  | EDA - Moderate Questions Q10-Q17 | Q10-Q13: City map, salary factors, field study, leadership |  | 3.3 | Jatin Rathod | 2026-07-06 | 2026-07-07 | 2026-07-07 | 6 | Completed | 100%
3.4.2 |  | EDA - Moderate Questions Q10-Q17 | Q14-Q17: Grad 2024, promo channels, DS events, quadrant salary |  | 3.4.1 | Jatin Rathod | 2026-07-07 | 2026-07-08 | 2026-07-08 | 6 | Completed | 100% | Quadrant analysis: 14.74L vs 12.83L
3.5 |  | EDA Notebook Assembly |  |  | 3.4 | Jatin Rathod | 2026-07-08 | 2026-07-08 | 2026-07-08 | 4 | Completed | 100% | Submitted 08-Jul-2026
3.5.1 |  | EDA Notebook Assembly | Compile Q&A, charts, markdown, summary table |  | 3.4 | Jatin Rathod | 2026-07-08 | 2026-07-08 | 2026-07-08 | 4 | Completed | 100% | DA_GPI_Analysis_JatinRathod.ipynb
4 | Monitoring & Reporting |  |  |  |  | Jatin Rathod | 2026-06-22 | 2026-08-01 | 2026-08-01 |  | Completed | 100%
4.1 |  | Weekly Status Reports |  |  |  | Jatin Rathod | 2026-06-22 | 2026-08-01 | 2026-08-01 | 8 | Completed | 100% | Submitted weekly on IAC platform
4.2 |  | Domain Lead Reviews |  |  |  | Jatin Rathod | 2026-06-22 | 2026-08-01 | 2026-08-01 | 4 | Completed | 100% | Weekly meetings attended
4.3 |  | RAID Log Updates |  |  |  | Jatin Rathod | 2026-06-22 | 2026-08-01 | 2026-08-01 | 2 | Completed | 100% | Issues resolved, risks monitored
5 | Week 5-7 - Analytics & Dashboard |  |  |  |  | Jatin Rathod | 2026-07-09 | 2026-07-23 | 2026-07-23 |  | Completed | 100%
5.1 |  | Power BI Dashboard |  |  | 3.5 | Jatin Rathod | 2026-07-09 | 2026-07-11 | 2026-07-11 | 6 | Completed | 100%
5.1.1 |  | Power BI Dashboard | Import dataset, create KPI cards |  |  | Jatin Rathod | 2026-07-09 | 2026-07-10 | 2026-07-10 | 3 | Completed | 100% | 5 KPIs: students, GPA, salary, Python, cities
5.1.2 |  | Power BI Dashboard | Build 6 charts, drill-through, tooltips |  | 5.1.1 | Jatin Rathod | 2026-07-10 | 2026-07-11 | 2026-07-11 | 3 | Completed | 100% | Submitted as .png dashboard
5.2 |  | Demo Video Recording |  |  | 3.5 | Jatin Rathod | 2026-07-18 | 2026-07-19 | 2026-07-19 | 4 | Completed | 100%
5.2.1 |  | Demo Video Recording | Write script (6 sections) |  |  | Jatin Rathod | 2026-07-18 | 2026-07-18 | 2026-07-18 | 2 | Completed | 100%
5.2.2 |  | Demo Video Recording | Record and finalize video (8 min) |  | 5.2.1 | Jatin Rathod | 2026-07-19 | 2026-07-19 | 2026-07-19 | 2 | Completed | 100% | Submitted on IAC hub
6 | Week 7-8 - Project Closure |  |  |  |  | Jatin Rathod | 2026-07-09 | 2026-08-03 | 2026-08-03 |  | Completed | 100%
6.1 |  | Final Project Report |  |  | 3.5 | Jatin Rathod | 2026-07-09 | 2026-08-03 | 2026-08-03 | 12 | Completed | 100% | Submitted 03-Aug-2026
6.1.1 |  | Final Project Report | Write all 7 sections + 4 appendix tables |  | 3.5 | Jatin Rathod | 2026-07-09 | 2026-08-02 | 2026-08-02 | 10 | Completed | 100%
6.1.2 |  | Final Project Report | Cross-document review & consistency check |  | 6.1.1 | Jatin Rathod | 2026-08-02 | 2026-08-02 | 2026-08-02 | 2 | Completed | 100% | Fixed inconsistencies across documents
6.2 |  | IAC Platform Submission |  |  | 6.1 | Jatin Rathod | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2 | Completed | 100% | All deliverables uploaded
6.2.1 |  | IAC Platform Submission | Rename all files, upload to Domain Deliverables Hub |  | 6.1 | Jatin Rathod | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2 | Completed | 100% | All green checkmarks confirmed
6.3 |  | Experience Letter Request |  |  | 6.2 | Jatin Rathod | 2026-08-03 | 2026-08-03 | 2026-08-03 | 1 | Completed | 100%
6.3.1 |  | Experience Letter Request | Send request to Harshada Topale |  | 6.2 | Jatin Rathod | 2026-08-03 | 2026-08-03 | 2026-08-03 | 1 | Completed | 100% | With full internship summary
Note on H7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: @Nirbhey Singh Pahwa - I was thinking if we should add an actual start date column as well? Reply: Or, let's call this one as planned start date and the next one as start date. The same can be done for End date. Because, writing 'actual' feels as if we've missed some deadline of some sorts so can be avoided. You can have this in the DM Goals template for now, let me add this to the next version of this template, i.e., Goals [Template v0.5] Thank you

## EXAMPLE
PROJECT PLAN
DOCUMENT VERSION: 1.0 | [6 empty] | INSTRUCTION TO USE THE PROJECT PLAN TEMPLATE: • All fields must be duly filled • The tasks/ activities listed in the template are bare minimum tasks and are not exhaustive. You will be required to add tasks/ activities based on the technology and the respective problem statement. • Clear all the sample data provided in the template. The data provided is only for reference purposes. • Mention the features you are working on the ”task name” field. • Mention the resource name who is responsible for completing a particular feature in the “assigned to” field. • Mention the start date and end date of a particular feature in the “start date” and “end date” field respectively. • Mention the time duration for completing a specific task in the “duration in days” field. • Select the current status of the feature you are working on from the drop-down list provided in the “status” field.
PROJECT NAME | Job Cloud |  |  | PLEASE GO THROUGH THE INSTRUCTION SHEET PROVIDED ON THE RIGHT HAND SIDE TO GET AN UNDERSTANDING OF HOW TO USE THIS TEMPLATE.
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | Job Cloud Job Portal
PROJECT SCOPE
PROJECT START DATE | 2020-01-01
PROJECT END DATE | 2020-01-04
OVERALL PROGRESS | In Progress
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
1 Initiation
| 1.1 Identify business problem |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.2 Recruit a team |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.3 Create a project charter |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
| 1.4 Requirement gathering |  | 2020-01-01 | 2020-04-01 | 3 | COMPLETED
2 Planning
| 2.1 Approval of business process |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.2 Baseline project plan |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
| 2.3 Team roles and responsibilities |  | 2020-05-01 | 2020-10-01 | 5 | COMPLETED
3 Execution
| 3.1 Finalize design |  | 2020-12-01 | 20/1/2020 | 8 | COMPLETED
| 3.2 Build |  | 22/1/2020 | 22/3/2020 | 59 | IN PROGRESS
| 3.2.1 Features |  | 22/1/2020 | 31/1/2020 | 9
Registration of candidate and employer
Login for candidate and employer
| Home page layout |  | 2020-01-02 | 2020-10-02 | 10
Navigation bar with logo
Home
Jobs
| Candidates |  | 2020-11-02 | 15/2/2020 | 5
List of candidates with information
| Employer |  | 16/2/2020 | 21/2/2020 | 5
List of employers with information
Advance search bar
Keyoword
Upload resume
Job categories
| Job listing/ Job result page |  | 22/2/2020 | 26/2/2020 | 4
Employer name
Job category & type information
Date & location
Favorite
Apply filter & sort
| Apply for job/ Jobs tag |  | 26/2/2020 | 29/2/2020 | 3
Employer information
Deadline of application
Job details
Job description
Role
Required skills
| Footer |  | 2020-01-03 | 2020-09-03 | 8
Quick links for candidate & employer
Legal and company information
Social media follow
| Profile |  | 2020-10-03 | 15/3/2020 | 5
Dashboard
Job alerts
Applied jobs/Posted jobs
Favorite jobs/candidates
Basic information of candidate/employer
| Post job |  | 16/3/2020 | 22/3/2020 | 7
Job title and desciption
Job category and type
Required skills and application deadline
Salary and qualification
Location
| 3.3 Testing |  | 25/03/2020 | 31/3/2020 | 6
3.3.1 Manual testing
3.3.2 Automation testing
| 4 Closure |  | 2020-01-04 | 2020-01-04 | 1